## Project Summary
Healthcare Report & Vitals AI Platform - Azure Cloud DevOps Project Plan
Project Owner / AI Engineer | Shardul
Cloud Architect | Amol
DevOps Engineers | Priyadarshani; Vikas
Mentor | Bhanupriya
Collaborator | Shantanu Datta
Core Data Stores | Azure Blob Storage; Azure PostgreSQL; Vector Database
AI / Extraction | Azure AI Document Intelligence; Azure OpenAI
Phase 1 | Upload reports + vitals.csv → validate/classify → Blob Storage
Phase 2 | Azure Function trigger → extraction → SQL for structured reports/vitals; Vector DB for text; Blob for radiology images
Phase 3 | SQL comparison/trends + Blob radiology images + Vector DB semantic text retrieval → Azure OpenAI → progress notes
Neo4j | Not used
Role Allocation
Person | Role | Primary Responsibility | Support
Shardul | AI Engineer / Application Owner | FastAPI, extraction, data processing, vector search, Azure OpenAI, analysis and progress notes | All phases
Amol | Cloud Architect | Azure architecture, PostgreSQL, Blob, networking, identity, cloud design | Development + DevOps
Priyadarshani | DevOps Engineer | CI/CD, Functions deployment, event triggers, security, release automation | Cloud operations
Vikas | DevOps Engineer | IaC, monitoring, logging, backups, performance, operations | Cloud operations
Bhanupriya | Mentor | Technical guidance, reviews, architecture and delivery checkpoints | All phases
Shantanu Datta | Collaborator | Domain/project collaboration and review support | Development
Progress values | Use: Not Started / In Progress / Blocked / Completed

## Development Project Plan
Task ID | Task Name | Description | Project Phase | Assigned To | Collaborator | Mentor | Progress
D01 | Requirements & Architecture Review | Finalize end-to-end architecture, data flow, report types, vitals flow, SQL/vector/blob responsibilities, and acceptance criteria. | Phase 0 - Planning | Shardul | Shantanu Datta | Bhanupriya | Not Started
D02 | Azure Resource & Environment Design | Define resource groups, environments, naming standards, networking, identity, secrets, storage, PostgreSQL, AI Search/vector DB and monitoring requirements. | Phase 0 - Planning | Amol | Shardul | Bhanupriya | Not Started
D03 | Phase 1 - Upload API | Implement FastAPI upload flow for patient reports and vitals.csv with patient_id and admission_id validation. | Phase 1 - Upload & Store | Shardul | Priyadarshani | Bhanupriya | Not Started
D04 | Phase 1 - File Validation | Validate IDs, PDF/image/CSV formats, file size, required fields, and upload metadata. | Phase 1 - Upload & Store | Shardul | Vikas | Bhanupriya | Not Started
D05 | Phase 1 - Report Classification | Detect report type such as CBC, LFT, BMP, pathology, radiology, and identify date/time metadata. | Phase 1 - Upload & Store | Shardul | Amol | Bhanupriya | Not Started
D06 | Phase 1 - Blob Storage Structure | Create patient/admission/report/vitals folder conventions and store original PDFs, images, radiology files, and vitals.csv. | Phase 1 - Upload & Store | Amol | Shardul | Bhanupriya | Not Started
D07 | Phase 1 - Event Trigger | Configure Blob-created event flow so a new report or vitals.csv upload triggers Phase 2 processing. | Phase 1 - Upload & Store | Priyadarshani | Amol | Bhanupriya | Not Started
D08 | Phase 2 - Azure Function | Build the event-driven function that reads newly uploaded files, identifies file type, and starts the correct extraction pipeline. | Phase 2 - Extract & Store | Shardul | Priyadarshani | Bhanupriya | Not Started
D09 | Phase 2 - Document Intelligence | Integrate Document Intelligence for OCR, layout detection, table extraction, key-value extraction, and radiology text/image handling. | Phase 2 - Extract & Store | Shardul | Amol | Bhanupriya | Not Started
D10 | Phase 2 - Lab Report Extraction | Extract laboratory values, normalize units, map test names, clean values, and prepare structured patient report records. | Phase 2 - Extract & Store | Shardul | Vikas | Bhanupriya | Not Started
D11 | Phase 2 - Vitals CSV Processing | Parse vitals.csv, validate timestamps and values, normalize units, and prepare time-series records. | Phase 2 - Extract & Store | Shardul | Vikas | Bhanupriya | Not Started
D12 | Phase 2 - PostgreSQL patient_reports | Create and populate patient_reports table with shared patient_id and admission_id mapping fields plus report-specific structured data. | Phase 2 - Extract & Store | Amol | Shardul | Bhanupriya | Not Started
D13 | Phase 2 - PostgreSQL vitals | Create and populate vitals table with patient_id, admission_id, recorded_at, heart rate, BP, SpO2, temperature, respiratory rate, etc. | Phase 2 - Extract & Store | Amol | Shardul | Bhanupriya | Not Started
D14 | Phase 2 - Radiology Text Extraction | Extract radiology findings/impression text and chunk/clean it for semantic retrieval. | Phase 2 - Extract & Store | Shardul | Vikas | Bhanupriya | Not Started
D15 | Phase 2 - Radiology Image Storage | Save extracted X-ray/CT/MRI or other radiology images in Blob Storage with patient/admission/report metadata. | Phase 2 - Extract & Store | Amol | Priyadarshani | Bhanupriya | Not Started
D16 | Phase 2 - Vector Database | Generate embeddings for radiology text and report text, store metadata including patient_id and admission_id, and enable semantic search. | Phase 2 - Extract & Store | Shardul | Amol | Bhanupriya | Not Started
D17 | Data Mapping & Validation | Verify patient_id and admission_id consistently map vitals, laboratory reports, radiology text, and radiology images to the correct patient/admission. | Phase 2 - Validation | Shardul | Vikas | Bhanupriya | Not Started
D18 | Phase 3 - Data Retrieval | Retrieve current/historical lab reports and vitals from PostgreSQL, radiology images from Blob, and radiology/report text from the vector database. | Phase 3 - Analysis | Shardul | Amol | Bhanupriya | Not Started
D19 | Phase 3 - Report & Vitals Comparison | Compare current versus historical laboratory values and analyze vitals trends over time. | Phase 3 - Analysis | Shardul | Vikas | Bhanupriya | Not Started
D20 | Phase 3 - Radiology Context Retrieval | Use semantic search to retrieve relevant radiology and report text for a selected patient and admission. | Phase 3 - Analysis | Shardul | Amol | Bhanupriya | Not Started
D21 | Phase 3 - Azure OpenAI Analysis | Combine SQL trends, vitals, radiology findings, retrieved report text, and patient context for AI-assisted summarization. | Phase 3 - Analysis | Shardul | Amol | Bhanupriya | Not Started
D22 | Progress Notes Generation | Generate structured progress notes containing patient summary, lab/vitals trends, radiology findings, and clinical insights. | Phase 3 - Output | Shardul | Shantanu Datta | Bhanupriya | Not Started
D23 | Dashboard & Visualization | Display patient information, lab comparison, vitals trends, radiology images, and generated progress notes. | Phase 3 - Output | Shardul | Vikas | Bhanupriya | Not Started
D24 | End-to-End Testing | Test report upload through extraction, database/vector/blob storage, retrieval, comparison, and progress-note generation. | Phase 4 - Testing | Shardul | Priyadarshani; Vikas; Amol | Bhanupriya | Not Started
D25 | Security & PHI Review | Review RBAC, authentication, authorization, PHI handling, audit requirements, secrets, and secure data access. | Phase 4 - Testing | Amol | Priyadarshani | Bhanupriya | Not Started

## Azure Cloud DevOps Plan
Task ID | Task Name | Description | Project Phase | Assigned To | Collaborator | Mentor | Progress
C01 | Cloud Landing Zone & Resource Groups | Define Dev/Test/Prod resource groups, Azure subscription structure, naming standards, tags, regions, and ownership. | Cloud Architecture | Amol | Shardul | Bhanupriya | Not Started
C02 | Azure Blob Storage Architecture | Configure containers, folder conventions, lifecycle policies, access controls, private endpoints, and retention for reports/vitals/radiology images. | Cloud Architecture | Amol | Priyadarshani | Bhanupriya | Not Started
C03 | Azure PostgreSQL Architecture | Provision PostgreSQL, configure networking, schema deployment, backup, scaling, connection security, and database monitoring. | Cloud Architecture | Amol | Vikas | Bhanupriya | Not Started
C04 | Vector Search Architecture | Select/configure vector search service, define indexes, metadata fields, embedding strategy, semantic search, and access pattern. | Cloud Architecture | Amol | Shardul | Bhanupriya | Not Started
C05 | Azure Function Deployment Design | Define Function App hosting plan, runtime configuration, environment variables, triggers, scaling, retries, timeout, and deployment slots. | Cloud Architecture | Amol | Priyadarshani | Bhanupriya | Not Started
C06 | Document Intelligence Integration | Configure secure access to Document Intelligence, endpoint/keys or managed identity, quotas, retry handling, and application configuration. | Azure Integration | Shardul | Amol | Bhanupriya | Not Started
C07 | Networking & Private Access | Design VNet integration, private endpoints, private DNS, subnet segmentation, NSGs, and secure service-to-service communication. | Networking | Amol | Priyadarshani; Vikas | Bhanupriya | Not Started
C08 | Identity & RBAC | Implement Microsoft Entra ID, managed identities, least-privilege RBAC, database/storage permissions, and separation of duties. | Security | Amol | Priyadarshani | Bhanupriya | Not Started
C09 | Secrets & Configuration Management | Move secrets and application configuration to Azure Key Vault and configure managed identity-based access. | Security | Priyadarshani | Amol | Bhanupriya | Not Started
C10 | CI/CD Pipeline | Create Git-based CI/CD for backend, Azure Functions, infrastructure/configuration, tests, and deployment to environments. | DevOps | Priyadarshani | Vikas; Shardul | Bhanupriya | Not Started
C11 | Infrastructure as Code | Automate Azure infrastructure using Bicep or Terraform with reusable modules and environment-specific parameters. | DevOps | Vikas | Amol | Bhanupriya | Not Started
C12 | Containerization & Registry (if required) | Containerize API/application components where appropriate and configure Azure Container Registry and deployment strategy. | DevOps | Vikas | Priyadarshani; Shardul | Bhanupriya | Not Started
C13 | Event-Driven Trigger Pipeline | Configure Blob upload events to Azure Function with reliable retries, dead-letter/error handling, idempotency, and duplicate-event protection. | DevOps | Priyadarshani | Amol; Shardul | Bhanupriya | Not Started
C14 | Application Monitoring | Configure Azure Monitor/Application Insights for APIs, Functions, latency, failures, dependency calls, and custom application metrics. | Monitoring | Vikas | Priyadarshani | Bhanupriya | Not Started
C15 | Centralized Logging | Configure Log Analytics, structured logs, correlation IDs, error tracking, and operational dashboards. | Monitoring | Vikas | Priyadarshani; Shardul | Bhanupriya | Not Started
C16 | Alerts & Operational Runbooks | Create alerts for function failures, storage errors, DB issues, high latency, failed deployments, and service health incidents. | Operations | Priyadarshani | Vikas | Bhanupriya | Not Started
C17 | Backup & Disaster Recovery | Configure PostgreSQL backups, Blob recovery/retention, recovery objectives, restore testing, and DR documentation. | Operations | Vikas | Amol | Bhanupriya | Not Started
C18 | Security Testing | Run configuration/security checks for storage, APIs, databases, identities, secrets, network exposure, and PHI access boundaries. | Security | Priyadarshani | Amol; Vikas | Bhanupriya | Not Started
C19 | Performance & Cost Optimization | Review Function scaling, PostgreSQL sizing, Blob lifecycle, vector search usage, Document Intelligence calls, and Azure cost controls. | Optimization | Amol | Priyadarshani; Vikas | Bhanupriya | Not Started
C20 | Production Deployment | Execute production release, validate infrastructure, run smoke tests, verify triggers/data flow, and establish rollback procedure. | Release | Priyadarshani | Vikas; Amol; Shardul | Bhanupriya | Not Started
C21 | Cloud Operations Handover | Prepare architecture diagram, deployment guide, runbooks, monitoring guide, troubleshooting steps, ownership matrix, and final documentation. | Handover | Vikas | Amol; Priyadarshani; Shardul | Bhanupriya | Not Started